## About_This_Data
Field | Value
Company | Northstar Water Services - fictional water-pipe maintenance and service company
Reporting date | 2026-09-30
Scope | 120 Q3 2026 work orders, five sites. All identities and records are synthetic.
Meaning | Cost is cumulative recorded cost of all statuses; not a budget or productivity claim.
Rejoin | This input is a deterministic checkpoint, not proof of your Copilot output.

## Work_Orders
Work_Order_ID | Site | Job_Category | Priority | Status | Assigned_To | Opened_Date | Due_Date | Closed_Date | Estimated_Hours | Actual_Hours | Cost_SGD | Description
WO-2026-0001 | Woodlands Hub | Leak Repair | Low | Closed | Aisha Tan | 2026-09-25 | 2026-10-02 | 2026-09-30 | 2 | 1 | 90 | Leak Repair scheduled or reactive task 001
WO-2026-0002 | Woodlands Hub | Leak Repair | Medium | Closed | Ben Lim | 2026-09-24 | 2026-10-02 | 2026-09-30 | 3 | 2 | 125.5 | Leak Repair scheduled or reactive task 002
WO-2026-0003 | Woodlands Hub | Leak Repair | High | In Progress | Chloe Goh | 2026-09-23 | 2026-10-02 |  | 4 | 0 | 161 | Leak Repair scheduled or reactive task 003
WO-2026-0004 | Jurong Depot | Leak Repair | Critical | On Hold | Daniel Lee | 2026-09-22 | 2026-10-02 |  | 5 | 0 | 196.5 | Leak Repair scheduled or reactive task 004
WO-2026-0005 | Jurong Depot | Valve Repair | Low | New | Elena Ong | 2026-09-21 | 2026-10-02 |  | 6 | 0 | 232 | Valve Repair scheduled or reactive task 005
WO-2026-0006 | Jurong Depot | Valve Repair | Medium | Closed | Farid Rahman | 2026-09-20 | 2026-10-02 | 2026-09-30 | 7 | 6 | 267.5 | Valve Repair scheduled or reactive task 006
WO-2026-0007 | Tampines Centre | Valve Repair | High | Closed | Grace Ng | 2026-09-19 | 2026-10-02 | 2026-09-30 | 8 | 7 | 303 | Valve Repair scheduled or reactive task 007
WO-2026-0008 | Tampines Centre | Valve Repair | Critical | On Hold | Hari Kumar | 2026-09-18 | 2026-10-02 |  | 2 | 0 | 338.5 | Valve Repair scheduled or reactive task 008
WO-2026-0009 | Tampines Centre | Pipe Replacement | Low | New | Aisha Tan | 2026-09-17 | 2026-10-02 |  | 3 | 0 | 374 | Pipe Replacement scheduled or reactive task 009
WO-2026-0010 | Paya Lebar Office | Pipe Replacement | Medium | Cancelled | Ben Lim | 2026-09-16 | 2026-10-02 |  | 4 | 0 | 409.5 | Pipe Replacement scheduled or reactive task 010
WO-2026-0011 | Paya Lebar Office | Pipe Replacement | High | Closed | Chloe Goh | 2026-09-15 | 2026-09-22 | 2026-09-22 | 5 | 2 | 445 | Pipe Replacement scheduled or reactive task 011
WO-2026-0012 | Paya Lebar Office | Pipe Replacement | Critical | Closed | Daniel Lee | 2026-09-14 | 2026-09-22 | 2026-09-22 | 6 | 3 | 480.5 | Pipe Replacement scheduled or reactive task 012
WO-2026-0013 | Changi Workshop | Pump Service | Low | New |  | 2026-09-13 | 2026-09-22 |  | 7 | 0 | 516 | Pump Service scheduled or reactive task 013
WO-2026-0014 | Changi Workshop | Pump Service | Medium | Assigned | Farid Rahman | 2026-09-12 | 2026-09-22 |  | 8 | 0 | 90 | Pump Service scheduled or reactive task 014
WO-2026-0015 | Changi Workshop | Pump Service | High | In Progress | Grace Ng | 2026-09-11 | 2026-09-22 |  | 2 | 0 | 125.5 | Pump Service scheduled or reactive task 015
WO-2026-0016 | Woodlands Hub | Pump Service | Critical | Closed | Hari Kumar | 2026-09-10 | 2026-09-22 | 2026-09-23 | 3 | 7 | 161 | Pump Service scheduled or reactive task 016
WO-2026-0017 | Woodlands Hub | Meter Service | Low | Closed | Aisha Tan | 2026-09-09 | 2026-09-22 | 2026-09-23 | 4 | 8 | 196.5 | Meter Service scheduled or reactive task 017
WO-2026-0018 | Woodlands Hub | Meter Service | Medium | Assigned | Ben Lim | 2026-09-08 | 2026-09-22 |  | 5 | 0 | 232 | Meter Service scheduled or reactive task 018
WO-2026-0019 | Jurong Depot | Meter Service | High | In Progress | Chloe Goh | 2026-09-07 | 2026-09-22 |  | 6 | 0 | 267.5 | Meter Service scheduled or reactive task 019
WO-2026-0020 | Jurong Depot | Meter Service | Critical | Cancelled | Daniel Lee | 2026-09-06 | 2026-09-22 |  | 7 | 0 | 303 | Meter Service scheduled or reactive task 020
WO-2026-0021 | Jurong Depot | Leak Repair | Low | Closed | Elena Ong | 2026-09-05 | 2026-09-12 | 2026-09-14 | 8 | 3 | 338.5 | Leak Repair scheduled or reactive task 021
WO-2026-0022 | Tampines Centre | Leak Repair | Medium | Closed | Farid Rahman | 2026-09-04 | 2026-09-12 | 2026-09-14 | 2 | 4 | 374 | Leak Repair scheduled or reactive task 022
WO-2026-0023 | Tampines Centre | Leak Repair | High | In Progress | Grace Ng | 2026-09-03 | 2026-09-12 |  | 3 | 0 | 409.5 | Leak Repair scheduled or reactive task 023
WO-2026-0024 | Tampines Centre | Leak Repair | Critical | On Hold | Hari Kumar | 2026-09-02 | 2026-09-12 |  | 4 | 0 | 445 | Leak Repair scheduled or reactive task 024
WO-2026-0025 | Paya Lebar Office | Valve Repair | Low | New |  | 2026-09-01 | 2026-09-12 |  | 5 | 0 | 480.5 | Valve Repair scheduled or reactive task 025
WO-2026-0026 | Paya Lebar Office | Valve Repair | Medium | Closed | Ben Lim | 2026-08-31 | 2026-09-12 | 2026-09-10 | 6 | 8 | 516 | Valve Repair scheduled or reactive task 026
WO-2026-0027 | Paya Lebar Office | Valve Repair | High | Closed | Chloe Goh | 2026-08-30 | 2026-09-12 | 2026-09-10 | 7 | 9 | 90 | Valve Repair scheduled or reactive task 027
WO-2026-0028 | Changi Workshop | Valve Repair | Critical | On Hold | Daniel Lee | 2026-08-29 | 2026-09-12 |  | 8 | 0 | 125.5 | Valve Repair scheduled or reactive task 028
WO-2026-0029 | Changi Workshop | Pipe Replacement | Low | New | Elena Ong | 2026-08-28 | 2026-09-12 |  | 2 | 0 | 161 | Pipe Replacement scheduled or reactive task 029
WO-2026-0030 | Changi Workshop | Pipe Replacement | Medium | Cancelled | Farid Rahman | 2026-08-27 | 2026-09-12 |  | 3 | 0 | 196.5 | Pipe Replacement scheduled or reactive task 030
WO-2026-0031 | Woodlands Hub | Pipe Replacement | High | Closed | Grace Ng | 2026-08-26 | 2026-09-02 | 2026-09-01 | 4 | 4 | 232 | Pipe Replacement scheduled or reactive task 031
WO-2026-0032 | Woodlands Hub | Pipe Replacement | Critical | Closed | Hari Kumar | 2026-08-25 | 2026-09-02 | 2026-09-01 | 5 | 5 | 267.5 | Pipe Replacement scheduled or reactive task 032
WO-2026-0033 | Woodlands Hub | Pump Service | Low | New | Aisha Tan | 2026-08-24 | 2026-09-02 |  | 6 | 0 | 303 | Pump Service scheduled or reactive task 033
WO-2026-0034 | Jurong Depot | Pump Service | Medium | Assigned | Ben Lim | 2026-08-23 | 2026-09-02 |  | 7 | 0 | 338.5 | Pump Service scheduled or reactive task 034
WO-2026-0035 | Jurong Depot | Pump Service | High | In Progress | Chloe Goh | 2026-08-22 | 2026-09-02 |  | 8 | 0 | 374 | Pump Service scheduled or reactive task 035
WO-2026-0036 | Jurong Depot | Pump Service | Critical | Closed | Daniel Lee | 2026-08-21 | 2026-09-02 | 2026-09-02 | 2 | 9 | 409.5 | Pump Service scheduled or reactive task 036
WO-2026-0037 | Tampines Centre | Meter Service | Low | Closed | Elena Ong | 2026-08-20 | 2026-09-02 | 2026-09-02 | 3 | 1 | 445 | Meter Service scheduled or reactive task 037
WO-2026-0038 | Tampines Centre | Meter Service | Medium | Assigned | Farid Rahman | 2026-08-19 | 2026-09-02 |  | 4 | 0 | 480.5 | Meter Service scheduled or reactive task 038
WO-2026-0039 | Tampines Centre | Meter Service | High | In Progress | Grace Ng | 2026-08-18 | 2026-09-02 |  | 5 | 0 | 516 | Meter Service scheduled or reactive task 039
WO-2026-0040 | Paya Lebar Office | Meter Service | Critical | Cancelled | Hari Kumar | 2026-08-17 | 2026-09-02 |  | 6 | 0 | 90 | Meter Service scheduled or reactive task 040
WO-2026-0041 | Paya Lebar Office | Leak Repair | Low | Closed | Aisha Tan | 2026-08-16 | 2026-08-23 | 2026-08-24 | 7 | 5 | 125.5 | Leak Repair scheduled or reactive task 041
WO-2026-0042 | Paya Lebar Office | Leak Repair | Medium | Closed | Ben Lim | 2026-08-15 | 2026-08-23 | 2026-08-24 | 8 | 6 | 161 | Leak Repair scheduled or reactive task 042
WO-2026-0043 | Changi Workshop | Leak Repair | High | In Progress | Chloe Goh | 2026-08-14 | 2026-08-23 |  | 2 | 0 | 196.5 | Leak Repair scheduled or reactive task 043
WO-2026-0044 | Changi Workshop | Leak Repair | Critical | On Hold | Daniel Lee | 2026-08-13 | 2026-08-23 |  | 3 | 0 | 232 | Leak Repair scheduled or reactive task 044
WO-2026-0045 | Changi Workshop | Valve Repair | Low | New | Elena Ong | 2026-08-12 | 2026-08-23 |  | 4 | 0 | 267.5 | Valve Repair scheduled or reactive task 045
WO-2026-0046 | Woodlands Hub | Valve Repair | Medium | Closed | Farid Rahman | 2026-08-11 | 2026-08-23 | 2026-08-25 | 5 | 1 | 303 | Valve Repair scheduled or reactive task 046
WO-2026-0047 | Woodlands Hub | Valve Repair | High | Closed | Grace Ng | 2026-08-10 | 2026-08-23 | 2026-08-25 | 6 | 2 | 338.5 | Valve Repair scheduled or reactive task 047
WO-2026-0048 | Woodlands Hub | Valve Repair | Critical | On Hold | Hari Kumar | 2026-08-09 | 2026-08-23 |  | 7 | 0 | 374 | Valve Repair scheduled or reactive task 048
WO-2026-0049 | Jurong Depot | Pipe Replacement | Low | New |  | 2026-08-08 | 2026-08-23 |  | 8 | 0 | 409.5 | Pipe Replacement scheduled or reactive task 049
WO-2026-0050 | Jurong Depot | Pipe Replacement | Medium | Cancelled | Ben Lim | 2026-08-07 | 2026-08-23 |  | 2 | 0 | 445 | Pipe Replacement scheduled or reactive task 050
WO-2026-0051 | Jurong Depot | Pipe Replacement | High | Closed | Chloe Goh | 2026-08-06 | 2026-08-13 | 2026-08-11 | 3 | 6 | 480.5 | Pipe Replacement scheduled or reactive task 051
WO-2026-0052 | Tampines Centre | Pipe Replacement | Critical | Closed | Daniel Lee | 2026-08-05 | 2026-08-13 | 2026-08-11 | 4 | 7 | 516 | Pipe Replacement scheduled or reactive task 052
WO-2026-0053 | Tampines Centre | Pump Service | Low | New | Elena Ong | 2026-08-04 | 2026-08-13 |  | 5 | 0 | 90 | Pump Service scheduled or reactive task 053
WO-2026-0054 | Tampines Centre | Pump Service | Medium | Assigned | Farid Rahman | 2026-08-03 | 2026-08-13 |  | 6 | 0 | 125.5 | Pump Service scheduled or reactive task 054
WO-2026-0055 | Paya Lebar Office | Pump Service | High | In Progress | Grace Ng | 2026-08-02 | 2026-08-13 |  | 7 | 0 | 161 | Pump Service scheduled or reactive task 055
WO-2026-0056 | Paya Lebar Office | Pump Service | Critical | Closed | Hari Kumar | 2026-08-01 | 2026-08-13 | 2026-08-12 | 8 | 2 | 196.5 | Pump Service scheduled or reactive task 056
WO-2026-0057 | Paya Lebar Office | Meter Service | Low | Closed | Aisha Tan | 2026-07-31 | 2026-08-13 | 2026-08-12 | 2 | 3 | 232 | Meter Service scheduled or reactive task 057
WO-2026-0058 | Changi Workshop | Meter Service | Medium | Assigned | Ben Lim | 2026-07-30 | 2026-08-13 |  | 3 | 0 | 267.5 | Meter Service scheduled or reactive task 058
WO-2026-0059 | Changi Workshop | Meter Service | High | In Progress | Chloe Goh | 2026-07-29 | 2026-08-13 |  | 4 | 0 | 303 | Meter Service scheduled or reactive task 059
WO-2026-0060 | Changi Workshop | Meter Service | Critical | Cancelled | Daniel Lee | 2026-07-28 | 2026-08-13 |  | 5 | 0 | 338.5 | Meter Service scheduled or reactive task 060
WO-2026-0061 | Woodlands Hub | Leak Repair | Low | Closed | Elena Ong | 2026-07-27 | 2026-08-03 | 2026-08-03 | 6 | 7 | 374 | Leak Repair scheduled or reactive task 061
WO-2026-0062 | Woodlands Hub | Leak Repair | Medium | Closed | Farid Rahman | 2026-07-26 | 2026-08-03 | 2026-08-03 | 7 | 8 | 409.5 | Leak Repair scheduled or reactive task 062
WO-2026-0063 | Woodlands Hub | Leak Repair | High | In Progress | Grace Ng | 2026-07-25 | 2026-08-03 |  | 8 | 0 | 445 | Leak Repair scheduled or reactive task 063
WO-2026-0064 | Jurong Depot | Leak Repair | Critical | On Hold | Hari Kumar | 2026-07-24 | 2026-08-03 |  | 2 | 0 | 480.5 | Leak Repair scheduled or reactive task 064
WO-2026-0065 | Jurong Depot | Valve Repair | Low | New | Aisha Tan | 2026-07-23 | 2026-08-03 |  | 3 | 0 | 516 | Valve Repair scheduled or reactive task 065
WO-2026-0066 | Jurong Depot | Valve Repair | Medium | Closed | Ben Lim | 2026-07-22 | 2026-08-03 | 2026-08-04 | 4 | 3 | 90 | Valve Repair scheduled or reactive task 066
WO-2026-0067 | Tampines Centre | Valve Repair | High | Closed | Chloe Goh | 2026-07-21 | 2026-08-03 | 2026-08-04 | 5 | 4 | 125.5 | Valve Repair scheduled or reactive task 067
WO-2026-0068 | Tampines Centre | Valve Repair | Critical | On Hold | Daniel Lee | 2026-07-20 | 2026-08-03 |  | 6 | 0 | 161 | Valve Repair scheduled or reactive task 068
WO-2026-0069 | Tampines Centre | Pipe Replacement | Low | New | Elena Ong | 2026-07-19 | 2026-08-03 |  | 7 | 0 | 196.5 | Pipe Replacement scheduled or reactive task 069
WO-2026-0070 | Paya Lebar Office | Pipe Replacement | Medium | Cancelled | Farid Rahman | 2026-07-18 | 2026-08-03 |  | 8 | 0 | 232 | Pipe Replacement scheduled or reactive task 070
WO-2026-0071 | Paya Lebar Office | Pipe Replacement | High | Closed | Grace Ng | 2026-07-17 | 2026-07-24 | 2026-07-26 | 2 | 8 | 267.5 | Pipe Replacement scheduled or reactive task 071
WO-2026-0072 | Paya Lebar Office | Pipe Replacement | Critical | Closed | Hari Kumar | 2026-07-16 | 2026-07-24 | 2026-07-26 | 3 | 9 | 303 | Pipe Replacement scheduled or reactive task 072
WO-2026-0073 | Changi Workshop | Pump Service | Low | New |  | 2026-07-15 | 2026-07-24 |  | 4 | 0 | 338.5 | Pump Service scheduled or reactive task 073
WO-2026-0074 | Changi Workshop | Pump Service | Medium | Assigned | Ben Lim | 2026-07-14 | 2026-07-24 |  | 5 | 0 | 374 | Pump Service scheduled or reactive task 074
WO-2026-0075 | Changi Workshop | Pump Service | High | In Progress | Chloe Goh | 2026-07-13 | 2026-07-24 |  | 6 | 0 | 409.5 | Pump Service scheduled or reactive task 075
WO-2026-0076 | Woodlands Hub | Pump Service | Critical | Closed | Daniel Lee | 2026-07-12 | 2026-07-24 | 2026-07-22 | 7 | 4 | 445 | Pump Service scheduled or reactive task 076
WO-2026-0077 | Woodlands Hub | Meter Service | Low | Closed | Elena Ong | 2026-07-11 | 2026-07-24 | 2026-07-22 | 8 | 5 | 480.5 | Meter Service scheduled or reactive task 077
WO-2026-0078 | Woodlands Hub | Meter Service | Medium | Assigned | Farid Rahman | 2026-07-10 | 2026-07-24 |  | 2 | 0 | 516 | Meter Service scheduled or reactive task 078
WO-2026-0079 | Jurong Depot | Meter Service | High | In Progress | Grace Ng | 2026-07-09 | 2026-07-24 |  | 3 | 0 | 90 | Meter Service scheduled or reactive task 079
WO-2026-0080 | Jurong Depot | Meter Service | Critical | Cancelled | Hari Kumar | 2026-07-08 | 2026-07-24 |  | 4 | 0 | 125.5 | Meter Service scheduled or reactive task 080
WO-2026-0081 | Jurong Depot | Leak Repair | Low | Closed | Aisha Tan | 2026-09-25 | 2026-10-02 | 2026-09-30 | 5 | 9 | 161 | Leak Repair scheduled or reactive task 081
WO-2026-0082 | Tampines Centre | Leak Repair | Medium | Closed | Ben Lim | 2026-09-24 | 2026-10-02 | 2026-09-30 | 6 | 1 | 196.5 | Leak Repair scheduled or reactive task 082
WO-2026-0083 | Tampines Centre | Leak Repair | High | In Progress | Chloe Goh | 2026-09-23 | 2026-10-02 |  | 7 | 0 | 232 | Leak Repair scheduled or reactive task 083
WO-2026-0084 | Tampines Centre | Leak Repair | Critical | On Hold | Daniel Lee | 2026-09-22 | 2026-10-02 |  | 8 | 0 | 267.5 | Leak Repair scheduled or reactive task 084
WO-2026-0085 | Paya Lebar Office | Valve Repair | Low | New |  | 2026-09-21 | 2026-10-02 |  | 2 | 0 | 303 | Valve Repair scheduled or reactive task 085
WO-2026-0086 | Paya Lebar Office | Valve Repair | Medium | Closed | Farid Rahman | 2026-09-20 | 2026-10-02 | 2026-09-30 | 3 | 5 | 338.5 | Valve Repair scheduled or reactive task 086
WO-2026-0087 | Paya Lebar Office | Valve Repair | High | Closed | Grace Ng | 2026-09-19 | 2026-10-02 | 2026-09-30 | 4 | 6 | 374 | Valve Repair scheduled or reactive task 087
WO-2026-0088 | Changi Workshop | Valve Repair | Critical | On Hold | Hari Kumar | 2026-09-18 | 2026-10-02 |  | 5 | 0 | 409.5 | Valve Repair scheduled or reactive task 088
WO-2026-0089 | Changi Workshop | Pipe Replacement | Low | New | Aisha Tan | 2026-09-17 | 2026-10-02 |  | 6 | 0 | 445 | Pipe Replacement scheduled or reactive task 089
WO-2026-0090 | Changi Workshop | Pipe Replacement | Medium | Cancelled | Ben Lim | 2026-09-16 | 2026-10-02 |  | 7 | 0 | 480.5 | Pipe Replacement scheduled or reactive task 090
WO-2026-0091 | Woodlands Hub | Pipe Replacement | High | Closed | Chloe Goh | 2026-09-15 | 2026-09-22 | 2026-09-23 | 8 | 1 | 516 | Pipe Replacement scheduled or reactive task 091
WO-2026-0092 | Woodlands Hub | Pipe Replacement | Critical | Closed | Daniel Lee | 2026-09-14 | 2026-09-22 | 2026-09-23 | 2 | 2 | 90 | Pipe Replacement scheduled or reactive task 092
WO-2026-0093 | Woodlands Hub | Pump Service | Low | New | Elena Ong | 2026-09-13 | 2026-09-22 |  | 3 | 0 | 125.5 | Pump Service scheduled or reactive task 093
WO-2026-0094 | Jurong Depot | Pump Service | Medium | Assigned | Farid Rahman | 2026-09-12 | 2026-09-22 |  | 4 | 0 | 161 | Pump Service scheduled or reactive task 094
WO-2026-0095 | Jurong Depot | Pump Service | High | In Progress | Grace Ng | 2026-09-11 | 2026-09-22 |  | 5 | 0 | 196.5 | Pump Service scheduled or reactive task 095
WO-2026-0096 | Jurong Depot | Pump Service | Critical | Closed | Hari Kumar | 2026-09-10 | 2026-09-22 | 2026-09-24 | 6 | 6 | 232 | Pump Service scheduled or reactive task 096
WO-2026-0097 | Tampines Centre | Meter Service | Low | Closed | Aisha Tan | 2026-09-09 | 2026-09-22 | 2026-09-24 | 7 | 7 | 267.5 | Meter Service scheduled or reactive task 097
WO-2026-0098 | Tampines Centre | Meter Service | Medium | Assigned | Ben Lim | 2026-09-08 | 2026-09-22 |  | 8 | 0 | 303 | Meter Service scheduled or reactive task 098
WO-2026-0099 | Tampines Centre | Meter Service | High | In Progress | Chloe Goh | 2026-09-07 | 2026-09-22 |  | 2 | 0 | 338.5 | Meter Service scheduled or reactive task 099
WO-2026-0100 | Paya Lebar Office | Meter Service | Critical | Cancelled | Daniel Lee | 2026-09-06 | 2026-09-22 |  | 3 | 0 | 374 | Meter Service scheduled or reactive task 100
WO-2026-0101 | Paya Lebar Office | Leak Repair | Low | Closed | Elena Ong | 2026-09-05 | 2026-09-12 | 2026-09-10 | 4 | 2 | 409.5 | Leak Repair scheduled or reactive task 101
WO-2026-0102 | Paya Lebar Office | Leak Repair | Medium | Closed | Farid Rahman | 2026-09-04 | 2026-09-12 | 2026-09-10 | 5 | 3 | 445 | Leak Repair scheduled or reactive task 102
WO-2026-0103 | Changi Workshop | Leak Repair | High | In Progress | Grace Ng | 2026-09-03 | 2026-09-12 |  | 6 | 0 | 480.5 | Leak Repair scheduled or reactive task 103
WO-2026-0104 | Changi Workshop | Leak Repair | Critical | On Hold | Hari Kumar | 2026-09-02 | 2026-09-12 |  | 7 | 0 | 516 | Leak Repair scheduled or reactive task 104
WO-2026-0105 | Changi Workshop | Valve Repair | Low | New | Aisha Tan | 2026-09-01 | 2026-09-12 |  | 8 | 0 | 90 | Valve Repair scheduled or reactive task 105
WO-2026-0106 | Woodlands Hub | Valve Repair | Medium | Closed | Ben Lim | 2026-08-31 | 2026-09-12 | 2026-09-11 | 2 | 7 | 125.5 | Valve Repair scheduled or reactive task 106
WO-2026-0107 | Woodlands Hub | Valve Repair | High | Closed | Chloe Goh | 2026-08-30 | 2026-09-12 | 2026-09-11 | 3 | 8 | 161 | Valve Repair scheduled or reactive task 107
WO-2026-0108 | Woodlands Hub | Valve Repair | Critical | On Hold | Daniel Lee | 2026-08-29 | 2026-09-12 |  | 4 | 0 | 196.5 | Valve Repair scheduled or reactive task 108
WO-2026-0109 | Jurong Depot | Pipe Replacement | Low | New |  | 2026-08-28 | 2026-09-12 |  | 5 | 0 | 232 | Pipe Replacement scheduled or reactive task 109
WO-2026-0110 | Jurong Depot | Pipe Replacement | Medium | Cancelled | Farid Rahman | 2026-08-27 | 2026-09-12 |  | 6 | 0 | 267.5 | Pipe Replacement scheduled or reactive task 110
WO-2026-0111 | Jurong Depot | Pipe Replacement | High | Closed | Grace Ng | 2026-08-26 | 2026-09-02 | 2026-09-02 | 7 | 3 | 303 | Pipe Replacement scheduled or reactive task 111
WO-2026-0112 | Tampines Centre | Pipe Replacement | Critical | Closed | Hari Kumar | 2026-08-25 | 2026-09-02 | 2026-09-02 | 8 | 4 | 338.5 | Pipe Replacement scheduled or reactive task 112
WO-2026-0113 | Tampines Centre | Pump Service | Low | New | Aisha Tan | 2026-08-24 | 2026-09-02 |  | 2 | 0 | 374 | Pump Service scheduled or reactive task 113
WO-2026-0114 | Tampines Centre | Pump Service | Medium | Assigned | Ben Lim | 2026-08-23 | 2026-09-02 |  | 3 | 0 | 409.5 | Pump Service scheduled or reactive task 114
WO-2026-0115 | Paya Lebar Office | Pump Service | High | In Progress | Chloe Goh | 2026-08-22 | 2026-09-02 |  | 4 | 0 | 445 | Pump Service scheduled or reactive task 115
WO-2026-0116 | Paya Lebar Office | Pump Service | Critical | Closed | Daniel Lee | 2026-08-21 | 2026-09-02 | 2026-09-03 | 5 | 8 | 480.5 | Pump Service scheduled or reactive task 116
WO-2026-0117 | Paya Lebar Office | Meter Service | Low | Closed | Elena Ong | 2026-08-20 | 2026-09-02 | 2026-09-03 | 6 | 9 | 516 | Meter Service scheduled or reactive task 117
WO-2026-0118 | Changi Workshop | Meter Service | Medium | Assigned | Farid Rahman | 2026-08-19 | 2026-09-02 |  | 7 | 0 | 90 | Meter Service scheduled or reactive task 118
WO-2026-0119 | Changi Workshop | Meter Service | High | In Progress | Grace Ng | 2026-08-18 | 2026-09-02 |  | 8 | 0 | 125.5 | Meter Service scheduled or reactive task 119
WO-2026-0120 | Changi Workshop | Meter Service | Critical | Cancelled | Hari Kumar | 2026-08-17 | 2026-09-02 |  | 2 | 0 | 161 | Meter Service scheduled or reactive task 120

## Technicians
Technician | Primary_Category | Available_Hours_Week | Home_Site
Aisha Tan | Leak Repair | 35 | Woodlands Hub
Ben Lim | Leak Repair | 30 | Jurong Depot
Chloe Goh | Leak Repair | 35 | Tampines Centre
Daniel Lee | Leak Repair | 30 | Paya Lebar Office
Elena Ong | Valve Repair | 35 | Changi Workshop
Farid Rahman | Valve Repair | 30 | Woodlands Hub
Grace Ng | Valve Repair | 35 | Jurong Depot
Hari Kumar | Valve Repair | 30 | Tampines Centre

## Control
Metric | Expected / control
Report_Date | 2026-09-30
total | 120
closed | 48
cancelled | 12
backlog | 60
overdue | 50
unassigned_backlog | 6
on_time_closed | 30
on_time_rate | 0.625
cost | 35827.5
Backlog definition | Status is neither Closed nor Cancelled
Overdue definition | Backlog and Due_Date strictly earlier than Report_Date
On-time definition | Closed_Date <= Due_Date; denominator Closed only
Unknown assignment | Blank Assigned_To stays blank; propose separately

## Prompt_Log
Step | App / mode | Prompt | What Copilot did | How I verified | Decision
Step 1 | EXCEL - CHAT ONLY | EXCEL - CHAT ONLY: Inspect this Northstar Water Services dashboard starter. Confirm tblWorkOrders, 120 unique IDs, reporting date 2026-09-30 and selection cells B2:B5 initially All. Explain which source and control sheets must remain intact. Report discrepancies before any edits.
Step 2 | EXCEL - PLAN | EXCEL - PLAN: Plan Dashboard for Northstar maintenance at 2026-09-30. Use selection cells B2:B5 for Site, Job_Category, Status, Assigned_To, all initially All. Reserve B7 total orders, B8 backlog, B9 overdue backlog, B10 closed, B11 on-time closure rate, B12 Cost_SGD. Place three charts for status, category and site with labels, units and scope. Preserve source data.
Step 3 | EXCEL - ALLOW EDITING | EXCEL - ALLOW EDITING: Build the planned six KPI formulas from tblWorkOrders. Backlog excludes Closed/Cancelled. Overdue also requires Due_Date < Control!B2. On-time rate counts Closed_Date <= Due_Date among Closed rows only, and shows N/A when none. Recorded cost sums Cost_SGD of all included statuses. Link to table columns, never a fixed 120-row range. Keep source data unchanged.
Step 4 | EXCEL - ALLOW EDITING | EXCEL - ALLOW EDITING: Create three editable bar or column charts using formula-backed summaries: work-order count by Status, by Job_Category and by Site. Each summary must reconcile to the total selected orders. Use white background, navy titles, blue/teal accents, readable labels and a visible reporting date. Do not use category counts as evidence of causes or use colour alone for status.
Step 5 | EXCEL - CHAT ONLY | EXCEL - CHAT ONLY: Reconcile the Northstar Water Services dashboard with Control at All selections. Compare all six KPIs and totals of the Status, Job_Category and Site charts. Flag hard-coded values, fixed row ranges, inconsistent scopes and any interpretation that treats job-category frequency as a cause. Do not edit.
Step 6 | EXCEL - CHAT ONLY | EXCEL - CHAT ONLY: Explain each Dashboard measure in plain English, including terminal statuses, strict overdue date rule, closed-only SLA denominator and meaning of recorded cost. Give one source-row example for overdue and one for on-time closure; cite Work_Order_ID. Do not guess a root cause or financial saving.

## Checks
Check | Formula / evidence | Result
Total clean rows

## Dashboard
Northstar Maintenance Dashboard | Selection | As at | 2026-09-30
Site | All
Job_Category | All
Status | All
Assigned_To | All
Measure | Current selection
Total work orders
Backlog
Overdue backlog
Closed
On-time closure rate
Cost SGD
Work orders by status | Count
New
Assigned
In Progress
On Hold
Closed
Cancelled
Work orders by category | Count
Leak Repair
Valve Repair
Pipe Replacement
Pump Service
Meter Service
Work orders by site | Count
Woodlands Hub
Jurong Depot
Tampines Centre
Paya Lebar Office
Changi Workshop

## Filter_Lists (hidden)
All | All | All | All
Woodlands Hub | Leak Repair | New | Aisha Tan
Jurong Depot | Valve Repair | Assigned | Ben Lim
Tampines Centre | Pipe Replacement | In Progress | Chloe Goh
Paya Lebar Office | Pump Service | On Hold | Daniel Lee
Changi Workshop | Meter Service | Closed | Elena Ong
|  | Cancelled | Farid Rahman
Grace Ng
Hari Kumar